## Slide 1: Lessons learned lecture #1
Private Sector Leased homes transfers
Jamie Ratcliff, Executive Director for People & Partnerships
22 April 2021

## Slide 2: Lessons learned lectures – the aim
Showcase learning opportunities as widely as possible so they can be applied to our day-to-day work.
Transparent by default – open session & post a video of the lecture, the slides and key learning points on our website.
Volunteers for future sessions to James.Mahaffy@networkhomes.org.uk
  Maria Moriarty - May
  Gabriel Codjoe - June
No names of any individuals or organisations or anything subject to active litigation– otherwise everything is potentially in scope to maximise the learning potential.

## Slide 3: Structure
The story
The lessons
The learning
Your turn
  Suggestions of additional learning points;
  Questions
  Discussion

## Slide 4: The story – part one
Private Sector Leasing (PSL) an integral part of London Strategic Housing (one of Network’s predecessor organisations) & important way of providing accommodation to homeless families nominated by London Borough partners.
January 2018 Network Homes Board decided to exit PSL business primarily due to complexity of operation, risk and impact on margin
‘Beauty parade’ selected housing association to transfer to in 2018, ready for transfer in May 2019
  Detailed discussions held with potentially transferring colleagues over a number of months
Transaction terminated in May 2019
Notes: Institutional investment (which requires Regulation) and grant (which also requires Regulation for rented homes) – can overcome gearing limits and works in current grant environment – if grant reduces then may not be sustainable long-term;
Taking on much more sales risk (which I’d argue we should combine with grant in the current environment) can keep gearing stable if we manage the market well – in reality we will not manage this perfectly and even if we do that would involve periods of ‘sitting it out’ so cannot be a steady pipeline
Institutional investment (which requires Regulation) – can’t get to the required hurdles without any grant in the current environment (which is arguable a low-water mark for global returns) – even if it could then because we are at a low-water mark would likely only work for the short-medium term.

## Slide 5: The story – part two
Alternative London-wide organisation selected for due diligence discussions in Summer 2019 – terminated in November 2019
Transfer to individual Boroughs then pursued as alternative
Technical breach of Tenant Involvement and Empowerment Standard in January 2020 – Network provided effective remedy, no serious detriment or follow-up by Regulator of Social Housing
First transfer completed in April 2020, last in August 2020
  Transfer of Undertakings (Protection of Employment) transfer to largest council in July.

## Slide 6: The lessons
Focus on people;
Communications;
Project management;
Regulatory Standards

## Slide 7: Focus on people
Residents & colleagues
Board helped focus - used to guide decision-making
Transferring colleagues experienced drawn-out uncertainty and unhappiness
Four different HR leads over time & no structured handover (see project management too)
In the end protected residents’ homes and colleagues employment

## Slide 8: Communications
Can never be too good;
Didn’t do enough to explain decision-making to colleagues and wider organisation;
Didn’t do enough to celebrate history or impact of PSL activity and place within Network;
Earlier and fuller communication needed on full range of impacts e.g. annual leave, tax implications
Colleagues experienced changing leads, uncertain times and evolving situation – all of which could have been improved (but not avoided entirely) by better communication.

## Slide 9: Project Management
Tried to do ‘on the fly’
  Project complexity increased over time
  Resource decreased
  Could not divert resources from managing the homes
  Multiple project managers
Lacked clear responsibilities, plan and oversight
No standardised documents or processes
No dedicated project team
Better coordination could have improved communication
Managed to mould/bend/adapt IT project management resource for wider application

## Slide 10: Regulatory Standards
Requirement to consult tenants on transfer of landlord identified in 2019
  May have been missed if initial transfer went through?
  Identified through Network’s quarterly assurance process
Discussed at board level, full oversight of decisions and implications
Changes to entity meant that the scope of consultation was moving
Letter did not catch-up with changes to proposals
  Consultation defective
Remedied through advice to former tenants as soon as possible
  No serious detriment or follow-up required by Regulator

## Slide 11: The learning – what we will do
Retain and enhance focus on residents – key part of immediate response project & training activity throughout the year
Focus colleague activity later in year on ‘reconnection’ – our internal relationships are really important
New corporate approach to project management – oversight, consistency but not bureaucracy – communication can never be too good
Regulatory standards – build on all staff briefings on Social Housing White Paper to ensure that all aware – increasing importance as serious detriment removed and fact requirements are changing
Review of contracts and HR policies for consistency, clarity and certainty.

## Slide 12: - Additional learning points, - Questions; & - Discussion
Your turn!